## WBS
WBS (TOKKI 실일정 v2) | [5 empty] | 주요 마일스톤 |  |  |  |  | 2주차 | [6 empty] | 3주차 | [6 empty] | 4주차 | [6 empty] | 5주차 | [6 empty] | 6주차
[6 empty] | 3/10 | 3/11~12 | 3/18~19 | 4/8~4/9 | 4/10 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
구분 | 역할분류 | 작업 | 기능상세 | 담당자 | 완료여부 | 착수 | 학습 | 산정 | 관리확정 | 제출 | 월 | 화 | 수 | 목 | 금 | 토 | 일 | 월 | 화 | 수 | 목 | 금 | 토 | 일 | 월 | 화 | 수 | 목 | 금 | 토 | 일 | 월 | 화 | 수 | 목 | 금 | 토 | 일 | 월 | 화 | 수 | 목 | 금
착수 | 팀장 | 프로젝트 킥오프 | 3/10 목표·역할·저장소 확정 | 팀장 | 완료 | ● | [28 empty] | 추 | 석 |  |  |  | 개
| 공통 | Agile/Scrum 학습 | 3/11~12 수업 기반 프로세스 정립 | 팀장/조원1/조원2/조원3 | 완료 |  | ● | [27 empty] | 연 | 휴 |  |  |  | 천
| 공통 | WBS/FP 산정 | 3/18~19 기능분해 및 규모 추정 | 팀장/조원1/조원2/조원3 | 완료 |  |  | ● | [31 empty] | 절
| 팀장 | 리스크/관리계획 확정 | 4/8~4/9 리스크표 및 통제프로세스 확정 | 팀장 | 완료 |  |  |  | ●
| 팀장 | 프로젝트 계획서 제출 | 4/10 제출본 확정 및 업로드 | 팀장 | 완료 |  |  |  |  | ●
| 조원1 | MVP 백엔드 구현 | 3/20~5/8 인증·퀴즈 API 중심 | 조원1 | 진행중
| 조원2 | MVP 프론트엔드 구현 | 3/20~5/8 카드/퀴즈 UI 중심 | 조원2 | 진행중
| 조원3 | MVP 통합/테스트 | 3/25~5/8 오답노트/관리자/통합 | 조원3 | 진행중
| 공통 | 중간고사 기간 | 4/13~4/25 신규 기능 개발 최소화 | 팀장/조원1/조원2/조원3 | 계획반영
| 팀장 | MVP 개발보고서 제출 | 5/8까지 MVP 보고서 제출 | 팀장 | 예정
| 공통 | 추가 요구사항 개발 | 5/9~5/29 Phase2/3 일부 반영 | 팀장/조원1/조원2/조원3 | 예정
| 팀장 | 추가요구사항 개발 완료 | 5/29 마감 | 팀장 | 예정
| FE | 프로젝트 생성 |  |  | 완료
| BE | 프로젝트 생성 |  |  | 완료
| FE | 프로젝트 설정 |  |  | 완료
| BE | 프로젝트 설정 |  |  | 완료
개발 | FE | 회원가입 | 회원가입 페이지 구현 |  | 작업대기
| BE |  | Google OAuth2 Clint 설정 |  | 작업대기
| BE |  | JWT 발급 검증 필터 구현 |  | 작업대기
| BE |  | 회원가입 로직 구현
| DB |  | 사용자, 관리자 테이블 구현 |  | 작업대기
| FE | 로그인 | 로그인/로그아웃 페이지 구현 |  | 작업대기
| BE |  | 관리자 role 칼럼 및 비밀 키 Service 구현 |  | 작업대기
| BE |  | 로그인 로직 구현 |  | 작업대기
| FE | 공통화면 구현 | 로딩창 페이지 구현 |  | 작업대기
| FE |  | 오류페이지 구현 |  | 작업대기
| FE |  | 서비스 소개 페이지 구현 |  | 작업대기
| FE | Phase 1 (MVP)-영단어 학습 탭 | 카드 컴포넌트 UI 구현 |  | 작업대기
| FE |  | 단어 API 구현 |  | 작업대기
| FE |  | 난이도() |  | 작업대기
| FE |  |  |  | 작업대기
배포 | DB | MySQL | 설치 및 환경 설정 |  | 작업대기
| DB |  | 데이터 베이스 생성 및 권한 부여 |  | 작업대기
| Server |  | 외부 연동 확인 |  | 작업대기
| BE | Back |  |  | 작업대기
| BE |  |  |  | 작업대기
| 공통 | Front | 도커 파일 작성 |  | 작업대기
| FE |  | nginx.conf 작성 |  | 작업대기
| FE |  | 서버 포트 설정 |  | 작업대기
데이터베이스 | DB | 스마트 컨트랙트 |  |  | 작업대기
| DB |  |  |  | 작업대기
| DB |  |  |  | 작업대기
| DB | 지갑 |  |  | 작업대기
| DB |  |  |  | 작업대기
| DB |  |  |  | 작업대기
유지보수 |  |  |  |  | 작업대기
작업대기
작업대기

## WBS_PERT_Integrated
WBS ID | Epic | Task | Owner | Predecessor | Start Date | End Date | Status | Optimistic(Day) | MostLikely(Day) | Pessimistic(Day) | Expected(Day) | Variance | Critical? | Note | 진척률(%) | 일정대비(%) | 일정헬스
0.1 | Initiation | Project kickoff and role setup | 팀장 | - | 2026-03-10 | 2026-03-10 | Done | 0.5 | 1 | 1.5 |  |  | Y | Start milestone
0.2 | Training | Agile/Scrum learning sessions | 팀장/조원1/조원2/조원3 | 0.1 | 2026-03-11 | 2026-03-12 | Done | 1 | 2 | 2.5 |  |  | Y | Methodology baseline
0.3 | Planning | WBS + FP sizing | 팀장/조원1/조원2/조원3 | 0.2 | 2026-03-18 | 2026-03-19 | Done | 1 | 2 | 3 |  |  | Y | Scope and effort estimate
0.4 | Planning | Risk and management finalization | 팀장 | 0.3 | 2026-04-08 | 2026-04-09 | Done | 0.5 | 1 | 2 |  |  | Y | Governance final
0.5 | Milestone | Project plan submission | 팀장 | 0.4 | 2026-04-10 | 2026-04-10 | Done | 0.2 | 0.5 | 1 |  |  | Y | Due date fixed
1.0 | Constraint | Midterm exam low-capacity period | 팀장/조원1/조원2/조원3 | 0.5 | 2026-04-13 | 2026-04-25 | Planned | 6 | 9 | 12 |  |  | Y | Only maintenance/light tasks
2.0 | MVP Backend | Auth + core quiz APIs | 조원1 | 0.5 | 2026-03-20 | 2026-05-02 | In Progress | 16 | 24 | 32 |  |  | Y | FR-01/02/04
2.1 | MVP Frontend | Card/quiz UI + API integration | 조원2 | 0.5 | 2026-03-20 | 2026-05-04 | In Progress | 16 | 24 | 34 |  |  | Y | FR-03/04
2.2 | MVP Fullstack | Wrong-note/admin/test integration | 조원3 | 2.0,2.1 | 2026-03-25 | 2026-05-06 | In Progress | 12 | 18 | 26 |  |  | Y | FR-05/07 + test
2.3 | MVP Milestone | MVP report completion | 팀장 | 2.2 | 2026-05-07 | 2026-05-08 | Planned | 1 | 2 | 3 |  |  | Y | Due by 5/8
3.0 | Phase2+ | Additional requirements development | 팀장/조원1/조원2/조원3 | 2.3 | 2026-05-09 | 2026-05-29 | Planned | 10 | 15 | 22 |  |  | Y | Extended features
3.1 | Final Milestone | Additional requirements deadline | 팀장 | 3.0 | 2026-05-29 | 2026-05-29 | Planned | 0.2 | 0.5 | 1 |  |  | Y | Due by 5/29
PERT Summary
Critical path (planned) | 0.1->0.2->0.3->0.4->0.5->1.0->2.0->2.2->2.3->3.0->3.1
Total expected duration (day)
Total variance
Std. deviation
Note | Midterm period (4/13~4/25) included as capacity constraint task.
Formulas:
일정대비(%) = IF(OR(ISBLANK([Start Date]),ISBLANK([End Date])),"",IF(TODAY()>=[End Date],100,IF(TODAY()<[Start Date],0,IF(ABS([End Date]-[Start Date])<0.0001,100,MIN(100,MAX(0,(TODAY()-[Start Date])/([End Date]-[Start Date])*100))))))
일정헬스 = IF([Status]="Done","완료",IF(OR(ISBLANK([Start Date]),ISBLANK([End Date])),"",IF(TODAY()>[End Date],"지연",IF(TODAY()<[Start Date],"예정","진행중"))))

## GoogleSheets_WBS_PERT
No | Category | ReqID | Work Item | Owner | Start | End | Dependency | Status | Priority | Progress(%) | Plan(%) | Health | Holiday/Sunday | Remarks
1 | Kickoff | - | 프로젝트 킥오프 및 역할 확정 | 팀장 | 2026-03-10 | 2026-03-10 | - | Done | High | 100 |  |  | 2026-03-15 일요일 2026-03-22 일요일 2026-03-29 일요일 2026-04-05 일요일 2026-04-12 일요일 2026-04-19 일요일 2026-04-26 일요일 2026-05-03 일요일 2026-05-05 어린이날 2026-05-10 일요일 2026-05-17 일요일 2026-05-24 부처님오신날 2026-05-25 대체공휴일 | 저장소/규칙 확정
2 | Methodology | - | Agile/Scrum 학습 및 운영규칙 확정 | 팀장/조원1/조원2/조원3 | 2026-03-11 | 2026-03-12 | 1 | Done | High | 100 |  |  |  | 수업 기반 운영 원칙 정리
3 | Planning | - | WBS/FP 산정 및 범위 확정 | 팀장/조원1/조원2/조원3 | 2026-03-18 | 2026-03-19 | 2 | Done | High | 100 |  |  |  | FP 스타일 기능분해
4 | Governance | - | 리스크 및 관리계획 확정 | 팀장 | 2026-04-08 | 2026-04-09 | 3 | Done | High | 100 |  |  |  | 리스크표/통제기준 확정
5 | Milestone | - | 프로젝트 계획서 제출 | 팀장 | 2026-04-10 | 2026-04-10 | 4 | Done | High | 100 |  |  |  | 과제 제출
6 | Constraint | - | 중간고사 기간: 신규개발 최소화 | 팀장/조원1/조원2/조원3 | 2026-04-13 | 2026-04-25 | 5 | Planned | High | 0 |  |  |  | 유지보수/문서보완 중심
7 | Backend | FR-01,02,04 | 인증/난이도/퀴즈 API 구현 | 조원1 | 2026-03-20 | 2026-05-02 | 5 | In Progress | High | 70 |  |  |  | MVP 핵심 API
8 | Frontend | FR-03,04 | 단어카드/퀴즈 UI 및 연동 | 조원2 | 2026-03-20 | 2026-05-04 | 5 | In Progress | High | 65 |  |  |  | 모바일 반응형 포함
9 | Fullstack | FR-05,07 | 오답노트/관리자/통합 테스트 | 조원3 | 2026-03-25 | 2026-05-06 | 7,8 | In Progress | High | 55 |  |  |  | 통합 품질 확보
10 | Milestone | - | MVP 개발보고서 제출 | 팀장 | 2026-05-07 | 2026-05-08 | 9 | Planned | High | 0 |  |  |  | 5/8 마감
11 | Phase2+ | FR-06,07,08 | 추가요구사항 개발 | 팀장/조원1/조원2/조원3 | 2026-05-09 | 2026-05-29 | 10 | Planned | Medium | 0 |  |  |  | 랭킹/PvP/고도화
12 | Milestone | - | 추가요구사항 개발 마감 | 팀장 | 2026-05-29 | 2026-05-29 | 11 | Planned | High | 0 |  |  |  | 5/29 최종
Formulas:
Plan(%) = IF(TODAY()>=[End],100,IF(TODAY()<[Start],0,IF(ABS([End]-[Start])<0.0001,100,MIN(100,MAX(0,(TODAY()-[Start])/([End]-[Start])*100)))))